## Project Profile
Defect Tracking Sheet
TC_02
Project ID | Group 2
Project Name | Expense Management System
Prepared/Modified by | Role | Date of Preparation
Gyan Shree |  | 2018-09-03
Reviewed by | Role | Date of Review
Meghana Patil |  | 2018-09-04
Approved by | Role | Date of Approval
Tanmaya K Acharya
Circulation List | ranu.singhal@capgemini.com ishani.basu@capgemini.com ram-gopal.padala@capgemini.com meghana.patil@capgemini.com mahitha.pochiraju@capgemini.com kartik.kashid@capgemini.com swati.e.mishra@capgemini.com gyan.shree@capgemini.com b-d.maneesha@capgemini.com
Version Number | 1

## Defect Tracking Sheet
Project ID: | Group 1 | Project Name : | Airline Reservation System | [21 empty] | VERIFIED
CLOSED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments |  | REOPENED | Coding |  |  | Internal Dev
D_01 | Update Project Code Module | Validation is missing in updation of Project Code | The fields which needs to be updated doesn't have any validation so that values in correct format gets inserted | Coding | STS | P2 | High | 1 | 1 | 2018-03-09 | Gyan Shree | Ranu Singhal | CLOSED | PPR | NA | Ishani Basu | 2018-03-09 | 2018-04-09 | Meghana Patil | 1 | 1 | NA | NA | SR | CNR | New Requirement | P2 | High | External QA
D_02 | Comment Section of deleteProjectCodeById | Return Type is missing | Need to mention return type as void | Coding | STS | Low | High | 1 | 1 | 2018-03-09 | Gyan Shree | Ranu Singhal | CLOSED | PPR | NA | Ishani Basu | 2018-03-09 | 2018-04-09 | Meghana Patil | 1 | 1 | NA | NA | RT | REP | Documentation | Low
D_03 | Comment Section in service layer | Author should be name | Need to mention name of the author | Coding | STS | Low | High | 1 | 1 | 2018-03-09 | Gyan Shree | Ranu Singhal | CLOSED | PPR | NA | Ishani Basu | 2018-03-09 | 2018-04-09 | Meghana Patil | 1 | 1 | NA | NA
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on G3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on H3: Prioritize the defect
Note on I3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on J3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on L3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on M3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on N3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on O3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on P3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on Q3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on R3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on S3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on T3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on U3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on V3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on X3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By