## ProjectName
Application | # | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Expense Maintenance System | 1 | Analysis | Requirement Analysis | 1 | 2018-08-27 | 2018-08-28 | 2 | 2018-08-27 | 2018-08-28 | Group 2 | Completed
|  |  | Preparing understanding document | 1 | 2018-08-27 | 2018-08-28 | 2 | 2018-08-27 | 2018-08-28 | Swati Mishra | Completed
|  |  | Updating QTS | 1 | 2018-08-27 | 2018-08-28 | 1 | 2018-08-27 | 2018-08-28 | Ishani Basu & Ranu Singhal | Completed
|  |  | Understanding HLD/Class Diagram Prep | 2 | 2018-08-28 | 2018-08-28 | 2 | 2018-08-28 | 2018-08-28 | Meghana Patil, Gyan Shree, Mahita Pochiraju, BD Maneesha | Completed
|  | Design | Unit Test Plan Preparation | 1 | 2018-08-28 | 2018-08-29 | 2 | 2018-08-28 | 2018-08-29 | Ram Padala | Completed
|  |  | LLD Preparation | 3 | 2018-08-29 | 2018-08-29 | 3 | 2018-08-29 | 2018-08-29
UTP Review
UTP Rework
LLD Review
|  | Build | Coding
Code Self Review
Self Testing
Rework
Code Peer Review
Peer Testing
Test Result review
Rework
Code Integration
Integration Testing
Rework
Test Result review
|  |  | Total Planned Hrs : |  |  | Total Actual Hrs: